## Slide 1
LEDIA BREGU, Director
Payment Systems, Accounting & Finance Department,
Bank of Albania, December 2021
Implementing the NRPS Strategy 2018-2023

## Slide 2: Action plans of NRPS completed during 2018-202
REGULATORY ENVIRONMENT FOR RP
- Transposition of PSD2 into PS Law, (agent, outsource)
- Strengthening the oversight of PS,
- Protect & Promote user rights, transparency & KYC
CUSTOMER-CENTRIC PAYMENT SERVICES
- Work in progress for PAD transposition (WB support)
- Offer a “basic” account product for unbanked
EXPANSION OF ACCESS POINTS & NETWORKS
- Developing the agent banking model (PSD2)
- Maintain a register of the agents & Update
IMPROVEMENTS TO INFRASTRUCTURES
- Operationalize “indirect participant” in the AECH.
- Operationalisation of AIPS-EURO system
- Feasibility study for switch/instant payments
- Implementation of the interbank DD scheme
- AIPS & AECH assessment vs the CPMI-IOSCO prsp
- Renovation of smart ID cards
STAKEHOLDER COMMITMENT
- Broaden the membership of the NPSC
- A more active and visible role for the NPSC
- Promote involvement of private sector in decisions
EFFECTIVENESS OF FINANCIAL LITERACY
- Increase public’s awareness on NRPS & its benefits
- Educate users on accounts & electronic payment instruments (work on National Financial Education Strategy)
LEVERAGING LARGE VOLUME PAYMENTS
- Increase the number & variety of public services (and P2G and B2G pmts) payable at e-Albania.
- Disbursement of social packages support via bank accounts;
EFFECTIVE BOA’S OVERSIGHT OF THE RETAIL PAYMENTS MARKET
- Revise oversight policy framework & manuals (to inc. PServices)
- Combined efforts of oversight with the supervision function
- Measure overarching objectives of NRPS once a year.
Notes: Strengthening Stakeholder Commitment
                Consolidation of a Conducive Regulatory Environment for Retail Payments
Improvements to payment and other infrastructure
Provision of Customer-Centric and Affordable Payment Instruments
Expansion of access Points and Networks for Payments
Improve the Effectiveness of Financial Literacy Efforts
Achieve Scale by Leveraging Large Volume Payment Programs
Effective BoA Oversight of the Retail Payments Market

## Slide 3: DIRECT DEBIT REGULATION REASONS AND OBJECTIVES
BoA’s Medium Term strategy and NRPS objective
Promotion of electronic payments and further enforcement of the
Law “On payment services”.
Enhancing EU Integration and aligning with SEPA Rules.
International and EU standardisation of processing messages.
Notes: Strengthening Stakeholder Commitment
Consolidation of a Conducive Regulatory Environment for Retail Payments
Improvements to payment and other infrastructure
Provision of Customer-Centric and Affordable Payment Instruments
Expansion of access Points and Networks for Payments
Improve the Effectiveness of Financial Literacy Efforts
Achieve Scale by Leveraging Large Volume Payment Programs
Effective BoA Oversight of the Retail Payments Market

## Slide 4: DIRECT DEBIT REGULATION – SCHEME and ACTORS
Creditor as a beneficiary of the payment (Utility Company)
Debtor as a payer (individual/ business that uses utility services)
Payment service provider of the creditor as a holder of the payment account of the creditor
Payment service provider of the debtor as a holder of the payment account of the debtor.
AECH system as a system where the direct debit instructions are cleared
AIPS system (RTGS) as a system where results of direct debit instructions are settled.
Intermediary payment service provider as an intermediary service provider between two payment service providers which are not participants in the AECH system.

## Slide 5: AIPS-EURO-Settlement of EURO payments in Albania
REASONS AND OBJECTIVES
National Retail Payment Strategy’s objective.
Aiming to reduce costs bared by banks and channelled to end users due to correspondent banking model and cash transactions handling on premises.
Reducing the processing time of transactions (RTGS).
Easier way to handle customers complains.
Better consumer protection as the transaction is processed domestically.
Regulated fees for end users aiming to promote financial inclusion the use of electronic payments and decrease informality.

## Slide 6: AIPS-EURO-Settlement of EURO payments in Albania
Entities that can participate and rules
In AIPS-EURO can participate all the banks already participating in AIPS-ALL.
Settlement account will be furnished through correspondent banks.
Liquidity is totally managed by banks - no additional facilities offered by BoA.
The system processes only MT103 - client transactions (individuals or businesses).
Costs for establishing and implementing the system are covered by BoA.
For banks there is not a annual fee for using the system – only per transaction fee
Limits for the commissions applied by banks to their clients:
 | Paper based transactions charges | Electronic transactions charges
Max limit allowed | 50 Eur | 25 Eur
Minimal limit allowed | Up to 6 Eur | Up to 3 eur
For transactions up to 10,000 € | 0.2% of the amount | 0.1% of the amount

## Slide 7: Action plans of NRPS still to be implemented 2022 -2023
REGULATORY ENVIRONMENT FOR RP
- PSD2 bylaws and Law enforcement 06/2022
CUSTOMER-CENTRIC PAYMENT SERVICES
- PAD transposition & enforcement
- Interoperability between all bank current & e-money accounts
- Re-design the existing pricing structure for current accounts
LEVERAGING LARGE VOLUME PAYMENTS
- Disbursement of pensions/all social assistance directly to the accounts of final beneficiaries.
- “Basic” bank accounts to be used;
- Expand the accepted payment instruments at e-Albania
EXPANSION OF ACCESS POINTS & NETWORKS
- Update register of the agents with new entrants
- Interoperability of the various channels and outlets
- Acquirers transparency on fees charged to merchants
- Systematical data on fees acquirers charge to merchants
EFFECTIVE BOA’S OVERSIGHT OF THE RETAIL PAYMENTS MARKET
- PSD2 bylaws and Law enforcement 06/2022
- Ensure PSP / PSO regularly review their cost & pricing structure.
- Ensure PSP / PSO avoid unfair/non-transparent pricing practices
EFFECTIVENESS OF FINANCIAL LITERACY
- Financial Education National Strategy
- Implementation of strategy (education & awareness)
- Measure the effectiveness of the financial education efforts
70%
70%
90%
80%
80%
70%
Notes: Strengthening Stakeholder Commitment
Consolidation of a Conducive Regulatory Environment for Retail Payments
Improvements to payment and other infrastructure
Provision of Customer-Centric and Affordable Payment Instruments
Expansion of access Points and Networks for Payments
Improve the Effectiveness of Financial Literacy Efforts
Achieve Scale by Leveraging Large Volume Payment Programs
Effective BoA Oversight of the Retail Payments Market

## Slide 8
06/2018 App
NATIONAL STRATEGY FOR RETAIL PAYMENTS 2018-2023 APPROVED IN NCPS
National Retail Payments Strategy 2018 – 2023 Objectives:
Increasing the current number of cashless payments per capita +130%
4.3 pmt /
capita
10 pmt /
capita
1
Achieving an adult account ownership ratio of 70%
2
The jointly approved strategy aims a material increase in Financial Inclusion and in cash-less payments
12/2021 Rev
4.3 pmt /
capita
9.7 pmt /
capita
Preliminary data as of 11/2021
66%

## Slide 9
Thank you for your attention !